## Sheet1
SPRINT 2
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#12 | #20 Using bootstrap and html, make a responsive navigation menu that will allow the user to navigate between the multiple pages of the car rental website | 1. Create and connect navigation menu that lead to the correct routes 2. Navigation menu is accessible to all devices and has different color | 2 | Low | Low- mostly because its gonna be access through desktop | Mohammed and Ba na,m | 2
#14 As a user, I want to be able to filter the vehicles based on the model, the price, the year, so that I can pick the vehicle that fits with my needs. | #18 Create a database for the vehicles and include the characteristics of the vehicles #19 Make an efficient sorting algorithms for the vehicles based on the year and the characteristics | 1. Develop an interface that will allow the users to pick which features of the vehicles is needed 2.Being able to sort the vehicles based on price, alphabetical order of manufacturer and model and year | 5 | High - The sorting system should be able to work and visible in the interface based on the type asked | High- one of the main task for car rental website | Yazid | 2
#15 As a customer service representative, I want to efficiently assist customers with or without reservations during the check-in procedure so that I can provide a seamless experience for the customer. | #22 Create a intuitive check-in interface for customer service to handle both reservation and non-reservation. (HTML and Bootstrap) | 1. Developed an interface that accommodate both reservation or non-reservation scenarios | 5 | High | High-main function of the website essential for CSR to handle reservation |  | 2 and 3
#16 As a system administrator, I want to efficiently manage user accounts, rental vehicles, and reservations so that i can ensure a secure and up-to-date system. | #23 Create an HTML/Bootstrap admin panel in Flask to manage user accounts, vehicle information, and reservations with a secure and user-friendly interface. Develop password policies for user account for better security(Flask/Python) | 1. Implement admin panel that handles user, vehicle and reservation (CRUD) | 5 | High | High- Necessary for system admin to manage all CRUD operations | Mohammed and yazid | 2
#17 As a user, I want to easily start a reservation and manage it, so that I can plan my trips with ease. | #24 Create a user-friendly interface in Flask for starting a reservation and implement a clear input fields for location, pick-up date etc... Create a reservation manager interface (view/modifiy/cancel) using HTML/Bootstrap/Flask | 1. Make a user friendly interface for starting a reservation, clear input fields and an intuitive vehicle selection process. 2. Displayed and provide clear and accessible view of existing reservation details with the options to modify and cancel. | 8-User should be able to make any reservation or modify their reservation | High | High - main function website | Mohammed and yazid | 2
SPRINT 3
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#35 As a customer, I want to easily locate the nearest branch for a convenient vehicle pickup and return, so that I can have a smooth car rental experience. | #36 Design an HTML/Bootstrap UI for customer input (postal code or airport location). Develop Flask/Python routes for accurate location identification and implement validation mechanism for postal code or airports location | 1. Provide a clear interface for customers to input either their postal code or airport location 2.Validate and handle different types of inputs, ensuring accuracy and reliability in location search 3. Display the exact pick-up and return date | 8 | High | High- Essential part of website since its the inital step of the car rental website | Mohammed and yazid | 3
#37 As a customer service representative, I want to efficiently handle customers during the check-in process, whether they have a reservation or not, in order to provide the best experience for customers | #38 Develop a HTML/Boostrap interface for check-in process that accommodate both reservation and non-reservations scenario. Develop Flask/Python backend for new reservation creation and reservation confirmation. Implement payment processing using both front and back end framework. | 1. Create UI check-in for both reservation and non-reservations scenario 3. Implement a rental agreement review process into the system for customers with their confirmed reservations 2. Implement payment processing with the confirmed reservations | 8 | High | High- since the check-in is implemented throughout all main function of the website it will affect the whole website | Mohammed and yazid | 3
#39 As a customer service representative, I want to efficiently manage the check-out process by reviewing rental agreements, processing final billing accurately, and confirming the completion of the return process so that I can ensure a smooth end to the customer's car rental experience. | #40 Design a HTML/Bootstrap UI for CSR to record and validate the vehicle inspection. Develop using both frontend and backend a interface for rental agreement review. Develop a Python/Flask logic for the billing calculation. Develop a Python/Flask logic to confirm the return process in the system. | 1. Develop UI record and validate the vehicle inspection 2. Implement final billing calculation and pay settlement 3. Confirm the completion of the return process | 8 | High | HIGh - Final step of the check in process (check-out). | Mohammed and yazid | 3
SPRINT 4
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (0,1,2,3,5,8) | Priority | Risk | Assign | Sprint
#58 As a customer, I want to provide feedback and ratings for rented vehicles and the overall rental experience so that I can share my opinions, and assist other customers in making informed decisions | #71 Develop frontend and backend feedback submission and validation using Flask routes and Bootstrap as UI. Display star rating and all customers review. | 1. Develop interface to submit feedback and ratings 2. Create the star or numerical rating system to capture customers experience 3.Ensure visibility of feedback to other customers for transparency | 5 | MED | MED- Essential to the website but wont affect the whole website functionality | Steven and David | 4
#13 As a business manager, I want to view the total sales for a specific month so that I can analyze the overall performance ,identify trends, and making informed decision for the car rental service. | #21 Develop Flask/Python functions for calculating and retrieving total sales data. Create a UI to make an HTML page using Bootstrap for better visualization of the monthly sales | 1. Provide clear and intuitive user interface for viewing monthly sales. 3. Make an option to select specifics months 2. Implement a visual representation in a form of graph or chart | 5 | MED | MED- This is just additional feature that will be explore but wont affect the website functionality | Steven and Ba nam | 4